## Search Committees 2022
MINISTRY SEARCH PROCESS
for Congregations in Search for August 2022
| Notes | Dates
Phase 1: Concluding a Ministry Well
Minister announces departure |  | Feb-Mar (recommended)
Congregations submits notice of ministerial transition |  | Feb-Mar
Consultation with Regional UUA staff/UUA transitions team |  | Feb-Mar
Church website update |  | Feb-June
Exit interviews |  | Mar-Aug
Interim ministry application and search |  | Mar-May
Interim ministry begins |  | Spring-Summer
Phase 2: Education and Preparation for Search
Board reviews congregational by-laws for UUA search process alignment |  | Winter 2021
Transitions Program Manager reviews search process with board |  | Feb-Apr 2021
Consultation with compensation consultants | recommended | Feb-Apr 2021
Approve budget for search committee |  | Spring 2021
Church website review |  | Spring 2021
Search committee selection |  | Apr-June 2021
Search committee reviews Settlement Handbook |  | Apr-June 2021
Phase 3: Building the Structure to Search
Transitions Program Manager assigns search committee retreat leader |  | Spring-Summer 2021
UUA transitions team hosts overview of search process | for boards and search committees | 2021-06-01
Search committee retreat |  | May-Aug 2021
Congregational record initiated: adds committee to email list/fair process covenant |  | May-Aug 2021
Congregational survey |  | July-Sep 2021
Negotiating team selected |  | Aug-Sep 2021
Cottage meetings/focus groups |  | Sep-Nov 2021
Beyond Categorical Thinking workshop |  | Sep-Dec 2021
Gather and create document packet |  | Sep-Dec 2021
Negotiating team recommends contract and compensation to board |  | Oct-Nov 2021
Copy of approved contract to Transitions Office |  | Oct-Nov 2021
Neutral pulpits selected |  | Fall 2021
Congregational record completed |  | mid-late Nov 2021
Phase 4: Opening Up the Search
Congregational record review by Transitions Program Manager, interim, & regional staff |  | mid-late Nov 2021
Congregational record approved and published |  | Nov 29-Dec 6
Packet approval by Transitions Program Manager |  | Dec (no later than Jan 1)
Consultation with Transitions Program Manager and approval to receive applicants |  | mid Dec-first week of Jan
Phase 5: Discernment/Mutual Selection
Receiving the initial list of applicants for the first offer date |  | Jan 2nd if approved
Initial references and websites |  | Jan 2-15 2022
Video/phone interviews of top applicants |  | mid-late Jan 2022
Last realistic date to expect names | search committee can extend | Jan 10-15 2022
Pre-canddiate selection |  | Mid Jan-early Feb 2022
Pre-candidate visits | Friday-Sunday | Feb 4-Mar 27 2022
Developed references (including UUA regional staff) |  | Feb 4-Mar 27 2022
List to Transitions Office | Ranked yeses/maybes/nos | by March 28, 2022
First offer date |  | March 31 (Noon EDT), 2022
Phase 6: Finalizing the Offer
Contract negotiations |  | March 31-mid April
Background checks |  | March 31-mid April
Announcing the candidate |  | early to mid April
Phase 7: Entering Into a New Ministry
Candidating week |  | April 24-May 1
Congregation submits Notice of Call |  | May-June 2022
Preparation for the August start |  | May-July 2022
Arrival |  | August 1st, 2022
Starting together |  | Aug-Nov 2022
If No Match Occurs by First Offer Date: The Second Offer Date
Board and search committee decide to prepare for second offer date |  | by April 8th, 2022
Ministers may apply to congregations preparing for second offer date |  | April 11th, 2022
Search committees receive applicant names for second offer date |  | April 15th, 2022
Last day for ministers to submit interest |  | April 23rd, 2022
Interviews and reference checks |  | mid to late April, 2022
Pre-candidating weekend |  | late April-May 2022
Candidating weekend |  | Late May-June 2022

## Ministers 2022
MINISTRY SEARCH PROCESS
for Ministers in Search for August 2022
| Notes | Dates
Subscribe to Updates about Settled Search Cycle (Transitions Office Newsletters) on MinistrySearch | required | July-Nov
Conversations with Transitions Director About Upcoming Search | recommended | July-Nov
Complete Ministerial Record on MinistrySearch |  | by Dec 31
Review Congregational Records & Draft Ministerial Agreements |  | by Dec 31
Conversations with Transitions Director About Congregational Interest | highly recommended | by Dec 31
Website |  | by Dec 31
Ministerial Record Review |  | by Dec 31
Submit Interests in Congregations for First Offer Date through MinistrySearch |  | Dec-mid Jan
References |  | by Dec 31
Last Realistic Date to Submit Name | check with Trans Office after this | Jan 10-15
Video Interviews |  | January
Pre-candidating Weekends |  | Feb 4-Mar 27
Developed References |  | Feb 4-Mar 27
Ranked List to Transitions Office | yeses/no/maybes | March 28th
First Offer Date |  | March 31st (nood EDT)
Contract Negotiations and Backgroud Checks |  | March 31st-Mid April
Informing Your Current Congregation/Ministry |  | April 1st
Candidating Week | recommended | April 24-May 1
Covenant with Interim Minister |  | May
Arrival |  | August 1st
If No Match Occurs: The Second Offer Date
Ministers May Express Interest in Congregations Preparing for Second Offer Date |  | April 11th, 2022
Search Committees Receive Names for Second Offer Date |  | April 15th, 2022
Last Day for Ministers to Submit Interest |  | April 23rd, 2022
Interviews | recommended | mid to late April, 2022
Pre-candidating Weekend | recommended | late April-May 2022
Candidating Weekend | recommended | Late May-June 2022

## Search Committees 2023
MINISTRY SEARCH PROCESS
for Congregations in Search for August 2023
| Notes | Dates
Phase 1: Concluding a Ministry Well
Minister announces departure | recommended | Feb-Mar 2021 (recommended)
Congregations submits notice of ministerial transition |  | Feb-Mar
Consultation with Regional UUA staff/UUA transitions team |  | Feb-Mar
Church website update |  | Feb-June
Exit interviews |  | Mar-Aug
Interim ministry application and search |  | Mar-May
Interim ministry begins |  | August 1st
Phase 2: Education and Preparation for Search
Board reviews congregational by-laws for UUA search process alignment |  | Winter 2022
Transitions Program Manager reviews search process with board |  | Feb-Apr 2022
Consultation with compensation consultants | recommended | Feb-Apr 2022
Approve budget for search committee |  | Spring 2022
Church website review |  | Spring 2022
Search committee selection |  | Apr-June 2022
Search committee reviews Settlement Handbook |  | Apr-June 2022
Phase 3: Building the Structure to Search
Transitions Program Manager assigns search committee retreat leader |  | Spring-Summer 2022
UUA transitions team hosts overview of search process | for boards and search committees | 2022-06-01
Search committee retreat |  | May-Aug 2022
Congregational record initiated: adds committee to email list/fair process covenant |  | May-Aug 2022
Congregational survey |  | July-Sep 2022
Negotiating team selected |  | Aug-Sep 2022
Cottage meetings/focus groups |  | Sep-Nov 2022
Beyond Categorical Thinking workshop |  | Sep-Dec 2022
Gather and create document packet |  | Sep-Dec 2022
Negotiating team recommends contract and compensation to board |  | Oct-Nov 2022
Copy of approved contract to Transitions Office |  | Oct-Nov 2022
Neutral pulpits selected |  | Fall 2022
Congregational record completed |  | mid-late Nov 2022
Phase 4: Opening Up the Search
Congregational record review by Transitions Program Manager, interim, & regional staff |  | mid-late Nov 2022
Congregational record approved and published |  | Nov 28-Dec 5
Packet approval by Transitions Program Manager |  | Dec (no later than Jan 1)
Consultation with Transitions Program Manager and approval to receive applicants |  | mid Dec-first week of Jan
Phase 5: Discernment/Mutual Selection
Receiving the initial list of applicants for the first offer date |  | Jan 2nd if approved
Initial references and websites |  | Jan 2-15 2023
Video/phone interviews of top applicants |  | mid-late Jan 2023
Last realistic date to expect names | search committee can extend | Jan 10-15 2023
Pre-canddiate selection |  | Mid Jan-early Feb 2023
Pre-candidate visits | Friday-Sunday | Feb 3-Mar 26 2023
Developed references (including UUA regional staff) |  | Feb 3-Mar 26 2023
List to Transitions Office | Ranked yeses/maybes/nos | by March 27, 2023
First offer date |  | March 30 (Noon EDT), 2023
Phase 6: Finalizing the Offer
Contract Negotiations |  | March 30-mid April
Background Checks |  | March 30-mid April
Announcing the Candidate |  | early to mid April
Phase 7: Entering Into a New Ministry
Candidating Week |  | April 23-April 30th
Congregation Submits Notice of Call |  | May-June 2023
Preparation for the August Start |  | May-July 2023
Arrival |  | August 1st, 2023
Starting Together |  | Aug-Nov 2023
If No Match Occurs: The Second Offer Date
Board and search committee decide to prepare for second offer date |  | by April 7th, 2023
Ministers may apply to congregations preparing for second offer date |  | April 10th, 2023
Search committees receive applicant names for second offer date |  | April 14th, 2023
Last day for ministers to submit interest |  | April 21th, 2023
Interviews and reference checks |  | mid to late April, 2023
Pre-candidating weekend |  | late April-May 2023
Candidating weekend |  | Late May-June 2023

## Ministers 2023
MINISTRY SEARCH PROCESS
for Ministers in Search for August 2023
| Notes | Dates
Subscribe to Updates about Settled Search Cycle (Transitions Office Newsletters) on MinistrySearch | required | July-Nov
Conversations with Transitions Director About Upcoming Search | recommended | July-Nov
Complete Ministerial Record on MinistrySearch |  | by Dec 31
Review Congregational Records & Draft Ministerial Agreements |  | by Dec 31
Conversations with Transitions Director About Congregational Interest | highly recommended | by Dec 31
Website |  | by Dec 31
Ministerial Record Review |  | by Dec 31
Submit Interests in Congregations for First Offer Date through MinistrySearch |  | Dec-mid Jan
References |  | by Dec 31
Last Realistic Date to Submit Name | check with Trans Office after this | Jan 10-15
Video Interviews |  | January
Pre-candidating Weekends |  | Feb 3-Mar 26
Developed References |  | Feb 3-Mar 26 | c
Ranked List to Transitions Office |  | March 27th
First Offer Date |  | March 30th (nood EDT)
Contract Negotiations and Backgroud Checks |  | March 30th-Mid April
Informing Your Current Congregation/Ministry |  | March 31st
Candidating Week | recommended | April 23-30
Covenant with Interim Minister |  | May
Arrival |  | August 1st
If No Match Occurs: The Second Offer Date
Ministers May Express Interest in Congregations Preparing for Second Offer Date |  | April 10th, 2023
Search Committees Receive Names for Second Offer Date |  | April 14th, 2023
Last Day for Ministers to Submit Interest |  | April 21th, 2023
Interviews | recommended | mid to late April, 2023
Pre-candidating Weekend | recommended | late April-May 2023
Candidating Weekend | recommended | Late May-June 2023

## Search Committees 2024
MINISTRY SEARCH PROCESS
for Congregations in Search for August 2024
| Notes | Dates
Phase 1: Concluding a Ministry Well
Minister announces departure | recommended | Feb-Mar 2022 (recommended)
Congregations submits notice of ministerial transition |  | Feb-Mar
Consultation with Regional UUA staff/UUA transitions team |  | Feb-Mar
Church website update |  | Feb-June
Exit interviews |  | Mar-Aug
Interim ministry application and search |  | Mar-May
Interim ministry begins |  | August 1st
Phase 2: Education and Preparation for Search
Board reviews congregational by-laws for UUA search process alignment |  | Winter 2023
Transitions Program Manager reviews search process with board |  | Feb-Apr 2023
Consultation with compensation consultants | recommended | Feb-Apr 2023
Approve budget for search committee |  | Spring 2023
Church website review |  | Spring 2023
Search committee selection |  | Apr-June 2023
Search committee reviews Settlement Handbook |  | Apr-June 2023
Phase 3: Building the Structure to Search
Transitions Program Manager assigns search committee retreat leader |  | Spring-Summer 2023
UUA transitions team hosts overview of search process | for boards and search committees | 2023-06-01
Search committee retreat |  | May-Aug 2023
Congregational record initiated: adds committee to email list/fair process covenant |  | May-Aug 2023
Congregational survey |  | July-Sep 2023
Negotiating team selected |  | Aug-Sep 2023
Cottage meetings/focus groups |  | Sep-Nov 2023
Beyond Categorical Thinking workshop |  | Sep-Dec 2023
Gather and create document packet |  | Sep-Dec 2023
Negotiating team recommends contract and compensation to board |  | Oct-Nov 2023
Copy of approved contract to Transitions Office |  | Oct-Nov 2023
Neutral pulpits selected |  | Fall 2023
Congregational record completed |  | mid-late Nov 2023
Phase 4: Opening Up the Search
Congregational record review by Transitions Program Manager, interim, & regional staff |  | mid-late Nov 2023
Congregational record approved and published |  | Nov 27-Dec 4
Packet approval by Transitions Program Manager |  | Dec (no later than Jan 1)
Consultation with Transitions Program Manager and approval to receive applicants |  | mid Dec-first week of Jan
Phase 5: Discernment/Mutual Selection
Receiving the initial list of applicants for the first offer date |  | Jan 2nd if approved
Initial references and websites |  | Jan 2-15 2024
Video/phone interviews of top applicants |  | mid-late Jan 2024
Last realistic date to expect names | search committee can extend | Jan 10-15 2024
Pre-canddiate selection |  | Mid Jan-early Feb 2024
Pre-candidate visits | Friday-Sunday | Feb 2-Mar 24 2024
Developed references (including UUA regional staff) |  | Feb 2-Mar 24 2024
List to Transitions Office | Ranked yeses/maybes/nos | by March 25, 2024
First offer date |  | March 28 (Noon EDT), 2024
Phase 6: Finalizing the Offer
Contract Negotiations |  | March 28-mid April
Background Checks |  | March 28-mid April
Announcing the Candidate |  | early to mid April
Phase 7: Entering Into a New Ministry
Candidating Week |  | April 21-April 28th
Congregation Submits Notice of Call |  | May-June 2024
Preparation for the August Start |  | May-July 2024
Arrival |  | August 1st, 2024
Starting Together |  | Aug-Nov 2024
If No Match Occurs: The Second Offer Date
Board and search committee decide to prepare for second offer date |  | by April 5th, 2024
Ministers may apply to congregations preparing for second offer date |  | April 12th, 2024
Search committees receive applicant names for second offer date |  | April 15th, 2024
Last day for ministers to submit interest |  | April 19th, 2024
Interviews and reference checks |  | mid to late April, 2024
Pre-candidating weekend |  | late April-May 2024
Candidating weekend |  | Late May-June 2024

## Ministers 2024
MINISTRY SEARCH PROCESS
for Ministers in Search for August 2024
| Notes | Dates
Subscribe to Updates about Settled Search Cycle (Transitions Office Newsletters) on MinistrySearch | required | July-Nov
Conversations with Transitions Director About Upcoming Search | recommended | July-Nov
Complete Ministerial Record on MinistrySearch |  | by Dec 31
Review Congregational Records & Draft Ministerial Agreements |  | by Dec 31
Conversations with Transitions Director About Congregational Interest | highly recommended | by Dec 31
Website |  | by Dec 31
Ministerial Record Review |  | by Dec 31
Submit Interests in Congregations for First Offer Date through MinistrySearch |  | Dec-mid Jan
References |  | by Dec 31
Last Realistic Date to Submit Name | check with Trans Office after this | Jan 10-15
Video Interviews |  | January
Pre-candidating Weekends |  | Feb 2-Mar 24
Developed References |  | Feb 2-Mar 24 | c
Ranked List to Transitions Office |  | March 25th
First Offer Date |  | March 28th (nood EDT)
Contract Negotiations and Backgroud Checks |  | March 28th-Mid April
Informing Your Current Congregation/Ministry |  | March 29th
Candidating Week | recommended | April 21-28
Covenant with Interim Minister |  | May
Arrival |  | August 1st
If No Match Occurs: The Second Offer Date
Ministers May Express Interest in Congregations Preparing for Second Offer Date |  | April 12th, 2024
Search Committees Receive Names for Second Offer Date |  | April 15th, 2024
Last Day for Ministers to Submit Interest |  | April 19th, 2024
Interviews | recommended | mid to late April, 2024
Pre-candidating Weekend | recommended | late April-May 2024
Candidating Weekend | recommended | Late May-June 2024

## Search Committees 2025
MINISTRY SEARCH PROCESS
for Congregations in Search for August 2025
| Notes | Dates
Phase 1: Concluding a Ministry Well
Minister announces departure | recommended | Feb-Mar 2023 (recommended)
Congregations submits notice of ministerial transition |  | Feb-Mar
Consultation with Regional UUA staff/UUA transitions team |  | Feb-Mar
Church website update |  | Feb-June
Exit interviews |  | Mar-Aug
Interim ministry application and search |  | Mar-May
Interim ministry begins |  | August 1st
Phase 2: Education and Preparation for Search
Board reviews congregational by-laws for UUA search process alignment |  | Winter 2024
Transitions Program Manager reviews search process with board |  | Feb-Apr 2024
Consultation with compensation consultants | recommended | Feb-Apr 2024
Approve budget for search committee |  | Spring 2024
Church website review |  | Spring 2024
Search committee selection |  | Apr-June 2024
Search committee reviews Settlement Handbook |  | Apr-June 2024
Phase 3: Building the Structure to Search
Transitions Program Manager assigns search committee retreat leader |  | Spring-Summer 2024
UUA transitions team hosts overview of search process | for boards and search committees | 2024-06-01
Search committee retreat |  | May-Aug 2024
Congregational record initiated: adds committee to email list/fair process covenant |  | May-Aug 2024
Congregational survey |  | July-Sep 2024
Negotiating team selected |  | Aug-Sep 2024
Cottage meetings/focus groups |  | Sep-Nov 2024
Beyond Categorical Thinking workshop |  | Sep-Dec 2024
Gather and create document packet |  | Sep-Dec 2024
Negotiating team recommends contract and compensation to board |  | Oct-Nov 2024
Copy of approved contract to Transitions Office |  | Oct-Nov 2024
Neutral pulpits selected |  | Fall 2024
Congregational record completed |  | mid-late Nov 2024
Phase 4: Opening Up the Search
Congregational record review by Transitions Program Manager, interim, & regional staff |  | mid-late Nov 2024
Congregational record approved and published |  | Dec 2- Dec 9
Packet approval by Transitions Program Manager |  | Dec (no later than Jan 1)
Consultation with Transitions Program Manager and approval to receive applicants |  | mid Dec-first week of Jan
Phase 5: Discernment/Mutual Selection
Receiving the initial list of applicants for the first offer date |  | Jan 2nd if approved
Initial references and websites |  | Jan 2-15 2025
Video/phone interviews of top applicants |  | mid-late Jan 2025
Last realistic date to expect names | search committee can extend | Jan 10-15 2025
Pre-canddiate selection |  | Mid Jan-early Feb 2025
Pre-candidate visits | Friday-Sunday | Feb 7-Mar 30 2025
Developed references (including UUA regional staff) |  | Feb 7-Mar 30 2025
List to Transitions Office | Ranked yeses/maybes/nos | by March 31, 2025
First offer date |  | April 3 (Noon EDT), 2025
Phase 6: Finalizing the Offer
Contract Negotiations |  | April 3-mid April
Background Checks |  | April 3-mid April
Announcing the Candidate |  | early to mid April
Phase 7: Entering Into a New Ministry
Candidating Week | recommended | April 27-May 4
Congregation Submits Notice of Call |  | May-June 2025
Preparation for the August Start |  | May-July 2025
Arrival |  | August 1st, 2025
Starting Together |  | Aug-Nov 2025
If No Match Occurs: The Second Offer Date
Board and search committee decide to prepare for second offer date |  | by April 5th, 2025
Ministers may apply to congregations preparing for second offer date |  | April 12th, 2025
Search committees receive applicant names for second offer date |  | April 15th, 2025
Last day for ministers to submit interest |  | April 19th, 2025
Interviews and reference checks |  | mid to late April, 2025
Pre-candidating weekend |  | late April-May 2025
Candidating weekend |  | Late May-June 2025

## Ministers 2025
MINISTRY SEARCH PROCESS
for Ministers in Search for August 2025
| Notes | Dates
Subscribe to Updates about Settled Search Cycle (Transitions Office Newsletters) on MinistrySearch | required | July-Nov
Conversations with Transitions Director About Upcoming Search | recommended | July-Nov
Complete Ministerial Record on MinistrySearch |  | by Dec 31
Review Congregational Records & Draft Ministerial Agreements |  | by Dec 31
Conversations with Transitions Director About Congregational Interest | highly recommended | by Dec 31
Website |  | by Dec 31
Ministerial Record Review |  | by Dec 31
Submit Interests in Congregations for First Offer Date through MinistrySearch |  | Dec-mid Jan
References |  | by Dec 31
Last Realistic Date to Submit Name | check with Trans Office after this | Jan 10-15
Video Interviews |  | January
Pre-candidating Weekends |  | Feb 7-Mar 30
Developed References |  | Feb 7-Mar 30
Ranked List to Transitions Office |  | March 31st
First Offer Date |  | April 3rd (nood EDT)
Contract Negotiations and Backgroud Checks |  | April 3rd-Mid April
Informing Your Current Congregation/Ministry |  | April 4th
Candidating Week | recommended | April 27-May 4
Covenant with Interim Minister |  | May
Arrival |  | August 1st
If No Match Occurs: The Second Offer Date
Ministers May Express Interest in Congregations Preparing for Second Offer Date |  | April 12th, 2025
Search Committees Receive Names for Second Offer Date |  | April 15th, 2025
Last Day for Ministers to Submit Interest |  | April 19th, 2025
Interviews | recommended | mid to late April, 2025
Pre-candidating Weekend | recommended | late April-May 2025
Candidating Weekend | recommended | Late May-June 2025